## Slide 1
Monitoring & Reporting: Financial Progress Report and Timesheet
COMCEC
COORDINATION
OFFICE
Ayşegül ÇERÇİ
Development and Investment Bank of Turkey
Senior Vice President
Customer Value Management & Business Development Department
  www.kalkinma.com.tr

## Slide 2
2
COMCEC
COORDINATION
OFFICE
LEGAL BASIS
“The COMCEC Strategy” and “Statute and Rules of Procedures of COMCEC” which were adopted by the 4th Extraordinary Session of the Islamic Summit held on 14-15 August 2012 in Mecca, Saudi Arabia.
Cooperation Protocol Between the COMCEC Coordination Office and the Development and Investment Bank of Turkey within the Framework of Financing and Monitoring provided under the COMCEC Project Funding.
PURPOSE and SCOPE
The purpose of the Contract is to define the rights, obligations and responsibilities of the Bank and Project Owner in the efficient and timely implementation process of the projects.
The Project Owner will be awarded the grant on the terms and conditions set out in the Contract.
  FUNDAMENTAL DOCUMENT: THE CONTRACT BETWEEN THE BANK AND THE PROJECT OWNERS

## Slide 3
3
COMCEC
COORDINATION
OFFICE
  GENERAL STRUCTURE & PROCESS FLOW
The Bank and CCO are not responsible for the implementation of project activities. Responsibility for the implementation of the project activities rests only with the PO.

## Slide 4
4
COMCEC
COORDINATION
OFFICE
The CCO and the Bank monitors the implementation of the Project in line with the Contract and the Guidelines.
The Bank performs efficient monitoring via document reviews, monitoring visits and on the spot checks in cooperation with the CCO.
The Bank also monitors project activities in terms of risks related to project implementation and informs the CCO accordingly if any problem occurs during project implementation.
The Bank provides information to the Coordination Committee about technical and financial progress of the Project.
  MONITORING & REPORTING
RIGHTS, OBLIGATIONS AND RESPONSIBILITIES OF THE BANK

## Slide 5
5
COMCEC
COORDINATION
OFFICE
  FINANCING THE PROJECT: THE ACCOUNT INFORMATION
If the aforementioned account is not opened before the signature of the Contract, Project Owner is obliged to inform the bank account number within 30 days after the signature date.
In case the Project Owner institution is not authorized to open/have a bank account regarding the relevant country legislation, an acceptable account number for the payments shall be informed to the Bank within 30 days after the signature date.
The Bank cannot be claimed for the payments, if the relevant account number is not stated in the Service Contract or it is not informed officially within the given time periods.
The Bank cannot be claimed for any additional cost which would arise due to incorrect bank account information provided by the Lead Project Owner, Project Coordinator or Trainers Researcher. Any additional cost would be offset from the payment in question.
The Project Owner, in any case, can not request additional financing that is not stated in the budget section of the project fiche.

## Slide 6
6
COMCEC
COORDINATION
OFFICE
  FINANCING THE PROJECT: TIMESHEETS
PO submits Timesheet(s) of the Project Coordinator and the Trainer(s) (if a training program is conducted in the respective month) within one week after the last day of each month during the project implementation period.
The Project Coordinator and the Trainer(s) shall prepare their own Timesheets which must be approved (checked and signed) by the Responsible Authority.
Timesheets provide a basis for payments to project personnel and show the weekly tasks performed by each project personnel in the relevant month. The number of days worked, location, detailed description of tasks, linkage with the activities and per diems of the project personnel must be stated in timesheets by considering the relevant budget items.
Timesheets should be prepared in accordance with the relevant Monthly Progress Report and Activity Report (if available).

## Slide 7
7
COMCEC
COORDINATION
OFFICE
  FINANCING THE PROJECT: FINANCIAL PROGRESS REPORTS
Financial Progress Report is the document that shows details about expenditures made during respective period. Financial Progress Report includes separate sheets for providing information regarding different expenditures in line with the project budget.
All expenditures should be stated in the relevant sheet using the USD/Local Currency exchange rate at the date of transaction. Necessary documents (invoices, etc.) that verify the expenditures will be attached to Financial Progress Report.
PO submits a Financial Progress Report within two weeks after the last day of the month if a main activity is undertaken in the respective month.
Financial Progress Report shall be prepared by Project Coordinator and approved (checked and signed) by Responsible Authority.

## Slide 8
COMCEC
COORDINATION
OFFICE
Addendum Form (Annex 8)
PO submits an Addendum Form (Annex 8) to request a change on the basics (work plan, activities, and transfer among budget items over 1.000 USD etc.) of the project.
However, the PO cannot make a transfer from other budget items to human resources item under any circumstances.
The Addendum Form, must be submitted at least one month before the respective activity is implemented.
Addendum Form is subject to approval of the CCO.
Notification Form (Annex 9)
PO submits a Notification Form for transfers between budget items up to 1.000 USD. The Form must be signed by the Contact Person and sent to the Bank.
8
  ADDENDUM PROCEDURE AND NOTIFICATION PROCESS

## Slide 9
COMCEC
COORDINATION
OFFICE
Responsible Authority shall initiate the addendum procedure if it wants to change the basics (work plan, activities, transfer between budget items etc.) of the project.
He/she must fill the Addendum Form (given in Annex Section) and convey it to CCO and the Bank for evaluation of the request.
The PO cannot transfer funds from other budget items to human resources budget item.
The Incidentals budget item can only be used upon the approval of the CCO and the Bank via addendum procedure.
The addendum request must be justified by rational explanations in order to be approved and it must be submitted to the CCO and the Bank at least a month before the respective activity.
9
  ADDENDUM PROCEDURE AND THE USE OF INCIDENTIALS BUDGET ITEM

## Slide 10
6
COMCEC
COORDINATION
OFFICE
Activity-Based Projects
Project Fiche (Annex 1)
Template for Declaration of the Responsible Authority of the Project Owner (Annex 2)
Monthly Progress Report Template (Annex 3)
Irregularity Report Template (Annex 4)
Financial Progress Report Template (Annex 5)
Timesheet Template for Project Coordinator and Trainer(s) (Annex 6)
Detailed Work Plan Template (Annex 7)
Addendum Form (Annex 8)
Notification Form (Annex 9)
Service Contract Template for Project Coordinator and Trainer(s) (Annex 10)
Template for Project Completion Report (Annex 11)
Activity Report Template (Annex 12)
Payment Control Form-Checklist tool for Financial Progress Report
THE CONTRACT ANNEXES
10

## Slide 11
11
COMCEC
COORDINATION
OFFICE
ANNEX- 6 TIMESHEETS
  TIMESHEETS

## Slide 12
12
COMCEC
COORDINATION
OFFICE
ANNEX- 6 TIMESHEETS
  TIMESHEETS

## Slide 13
13
COMCEC
COORDINATION
OFFICE
ANNEX-5 DISBURSEMENT REQUEST FORM
  FINANCIAL PROGRESS REPORT

## Slide 14
14
COMCEC
COORDINATION
OFFICE
DISBURSEMENT REQUEST FORM SAMPLE
  FINANCIAL PROGRESS REPORT

## Slide 15
15
COMCEC
COORDINATION
OFFICE
DISBURSEMENT REQUEST FORM-PART I
  FINANCIAL PROGRESS REPORT

## Slide 16
16
COMCEC
COORDINATION
OFFICE
DISBURSEMENT REQUEST FORM-PART II
  FINANCIAL PROGRESS REPORT

## Slide 17
17
COMCEC
COORDINATION
OFFICE
HUMAN RESOURCES
  FINANCIAL PROGRESS REPORT

## Slide 18
18
COMCEC
COORDINATION
OFFICE
HUMAN RESOURCES
  FINANCIAL PROGRESS REPORT

## Slide 19
19
COMCEC
COORDINATION
OFFICE
WORKSHOP
  FINANCIAL PROGRESS REPORT

## Slide 20
20
COMCEC
COORDINATION
OFFICE
WORKSHOP
  FINANCIAL PROGRESS REPORT

## Slide 21
21
COMCEC
COORDINATION
OFFICE
TRAINING
  FINANCIAL PROGRESS REPORT

## Slide 22
22
COMCEC
COORDINATION
OFFICE
TRAINING
  FINANCIAL PROGRESS REPORT

## Slide 23
23
COMCEC
COORDINATION
OFFICE
STUDY VISIT
  FINANCIAL PROGRESS REPORT

## Slide 24
24
COMCEC
COORDINATION
OFFICE
CONFERENCE AND SEMINAR
  FINANCIAL PROGRESS REPORT

## Slide 25
25
COMCEC
COORDINATION
OFFICE
ASSOCIATED INVESTMENT
  FINANCIAL PROGRESS REPORT

## Slide 26
26
COMCEC
COORDINATION
OFFICE
INCIDENTALS
  FINANCIAL PROGRESS REPORT

## Slide 27
27
COMCEC
COORDINATION
OFFICE
ANNEX- 8 ADDENDUM FORM
  ADDENDUM FORM

## Slide 28
28
COMCEC
COORDINATION
OFFICE
ANNEX- 8 ADDENDUM FORM
  ADDENDUM FORM

## Slide 29
29
COMCEC
COORDINATION
OFFICE
ANNEX- 9 NOTIFICATION FORM
  NOTOFICATION FORM

## Slide 30
30
COMCEC
COORDINATION
OFFICE
ANNEX- 9 NOTIFICATION FORM
  NOTOFICATION FORM

## Slide 31
31
COMCEC
COORDINATION
OFFICE
PAYMENT CONTROL FORM

## Slide 32
32
COMCEC
COORDINATION
OFFICE
ADDENDUM FORM

## Slide 33
33
COMCEC
COORDINATION
OFFICE
REVISED BUDGET

## Slide 34
34
COMCEC
COORDINATION
OFFICE
Documents that form basis for the payments/make significant changes in the Project are required to be delievered to the Bank in hard copy.
The Contract
Financial Progress Reports
  Financial Progress Report and it’s annexes (Report+Annexes+verifying expenditure documents-invoices, airfare tickest etc.)
Timesheets
Addendum Form (if applicable)
Notification Form (if applicable)
REPORTS/DOCUMENTS REQUIRED TO BE DELIVERED IN HARD COPY

## Slide 35
THANK YOu
COMCEC
COORDINATION
OFFICE
aysegul.cerci@kalkinma.com.tr
caner.kar@kalkinma.com.tr
selma.demirci@kalkinma.com.tr
naz.karabagli@kalkinma.com.tr
bankcpf@kalkinma.com.tr
cpf@comcec.org
35