## Slide 1
Reporting and Monitoring
April 8th, 2026
programs.comcec.org
Ali ORUÇ
Expert
COMCEC
COORDINATION
OFFICE

## Slide 2: Outline
2
COMCEC
COORDINATION
OFFICE
Importance of Reporting and Monitoring
Detailed Work Plan
Monthly Progress Report
Activity Report
Project Completion Report
Additional Reports for new Project Types:
Needs Assessment and Peer-to-Peer Experience Sharing

## Slide 3
3
COMCEC
COORDINATION
OFFICE
Observation of the physical and financial progress and following-up the results obtained, the collection and measurement of the information regarding the project.
Monitoring will be done via reporting as well as side-visits in the COMCEC Project Funding.
Reporting aims to measure how much of the project activities are completed.
Also, it aims to determine the achievements and problems during the implementation of the project.
Importance of Reporting and Monitoring

## Slide 4
4
COMCEC
COORDINATION
OFFICE
Corrective actions can be taken for problems and risks with the help of reporting.
The CCO and Bank could inform the Project Owner for timely decisions to support implementation.
Funds will be transferred following the reporting of the progress in the project (such as time-sheets, progress reports).
Importance of Reporting and Monitoring

## Slide 5
5
COMCEC
COORDINATION
OFFICE
Project activities and other preparatory works related to the activities will be presented in the Detailed Work Plan.
It will help to facilitate the time-management and following–up the activities.
It will be prepared by the Project Coordinator (PC sends Detailed Work Plan to the Bank within two weeks after signing service contract).
Trainer(s) (if available) is supposed to contribute to the preparation of the Detailed Work Plan.
Before transfer of the payments, the Bank checks the timesheets by considering Detailed Work Plan
Detailed Work Plan

## Slide 6
6
COMCEC
COORDINATION
OFFICE

## Slide 7
7
COMCEC
COORDINATION
OFFICE

## Slide 8
8
COMCEC
COORDINATION
OFFICE

## Slide 9
9
COMCEC
COORDINATION
OFFICE

## Slide 10
10
COMCEC
COORDINATION
OFFICE

## Slide 11
11
COMCEC
COORDINATION
OFFICE

## Slide 12: Monthly Progress Report
12
COMCEC
COORDINATION
OFFICE
Monthly Progress Report summarizes the technical progress of the project activities in the respective month.
It also includes details such as the problems encountered, the measures taken, and preparations for the next month.
The Bank and the CCO follow the progress regarding the project activities through Monthly Progress Report.
In case of any problem, report enables the CCO and Bank to intervene timely.

## Slide 13: Monthly Progress Report
13
COMCEC
COORDINATION
OFFICE
Monthly Progress Report is prepared and signed by the Project Coordinator and Responsible Authority
Contact Person checks the Monthly Progress Reports
Payments are made based on the Monthly Progress Reports

## Slide 14
14
COMCEC
COORDINATION
OFFICE

## Slide 15
15
COMCEC
COORDINATION
OFFICE

## Slide 16
16
COMCEC
COORDINATION
OFFICE

## Slide 17: Activity Report
17
COMCEC
COORDINATION
OFFICE
Activity Reports are to be prepared for the activities such as Training, Workshop, Seminar and Study Visit within two weeks after one of the activity is successfully completed and sent to the CCO for approval.
Aim of the Activity Report is to evaluate the success of the activity.
Activity Reports also provide input for the Project Completion Report.
Project Coordinator is responsible for drafting Activity Reports
Trainer(s) is/are responsible for contributing to the preparation of the Activity Reports ( if available).

## Slide 18
18
COMCEC
COORDINATION
OFFICE

## Slide 19
19
COMCEC
COORDINATION
OFFICE

## Slide 20
20
COMCEC
COORDINATION
OFFICE

## Slide 21
21
COMCEC
COORDINATION
OFFICE

## Slide 22: Project Completion Report
22
COMCEC
COORDINATION
OFFICE
The Project Completion Report is a closing report that provides general information on project activities, outputs and financial aspects. It aims to provide comprehensive information for third parties.
The Project Completion Report is prepared within two weeks after all activities are successfully completed and sent to the CCO for approval.
It is prepared and signed by the Project Coordinator and signed by the Responsible Authority.
Project Coordinator is responsible for drafting Project Completion Report
Contact Person checks the Project Completion Report
Last payments will be done after approval of the Project Completion Reports.

## Slide 23
23
COMCEC
COORDINATION
OFFICE

## Slide 24
24
COMCEC
COORDINATION
OFFICE

## Slide 25
25
COMCEC
COORDINATION
OFFICE

## Slide 26
26
COMCEC
COORDINATION
OFFICE

## Slide 27: Needs Assessment Report
27
COMCEC
COORDINATION
OFFICE
Assess needs of the PO Member Country and propose solutions to overcome the challenges and requirements of the member country in the related sector.
PO submits two drafts of the Needs Assessment Report in line with the template.
Section I - Assessing the Current Situation
Section II - Gathering and Analyzing Data
Section III - Making Decisions and Recommendations
Special Reports for Needs Assessment Projects

## Slide 28: Field Study Report
28
COMCEC
COORDINATION
OFFICE
In Peer-to-Peer Experience Sharing activities, the PO submits Field Study Report for reflecting the knowledge and experience acquired during the activity.
                Submit the 1st Section of the Field Study Report, (current situation of PO Country) before the visit
                Submit 2nd and 3rd sections after the activity (current situation in the host country and recommendations)
Special Reports for Peer-to-Peer Experience Sharing Projects

## Slide 29
THANKYOu
cpf.comcec.org
cpf@comcec.org
COMCEC
COORDINATION
OFFICE