## Slide 1
Critical Issues for Successful Implementation
April 8th, 2026
COMCEC Coordination Office
Eda AKÇA
Program Coordinator
Programs and Projects Department

## Slide 2: What is Critical?
Following the Rules
Effective Communication
Good Logistical Issues and Deadlines
National Ownership
2

## Slide 3
Following the Rules
Project Implementation Guidelines
Visibility Manual
1
3

## Slide 4
Project Implementation Guidelines is the main document detailing the rules and procedures of the COMCEC Project Funding
Includes information about responsibilities of actors and project personnel, institutional structure, implementation and financing procedures, monitoring etc.
Please read the Program Implementation Guidelines whenever needed during the project implementation.
Project Implementation
Guidelines
Following the Rules
4

## Slide 5
Sections to consider;
About the payments (see article 10. Payments - page 22 )
About irregularities and noncompliance (see article 9. Noncompliance and Related Santcions - page 21 )
About the monitoring and evaluation (see article 8. Reporting and Monitoring - page 17)
About the transfers between budget items (see article 8.8. Addendum Form - page 20 )
5
Project Implementation
Guidelines
Following the Rules

## Slide 6
Visibility Manual
Visibility Manual aims to raise the awareness of specific or general audience about the COMCEC and COMCEC funded projects.
The Manual mainly covers the written and visual identity of the COMCEC.
Setting out requirements and guidelines for briefings, written materials, press conferences, presentations, flyers, flags, invitations, signs, commemorative plaques and all other tools used to highlight COMCEC support.
6
Following the Rules

## Slide 7
The COMCEC Logo must be used in all COMCEC- funded activities in line with the rules cited in this manual.
All visibility materials must be in English. POs can use the local language, Arabic and French in addition to English.
Graphics and wording of the visibility material must be visible, legible and clear at all times.
The visibility materials must be in compliant with the samples demonstrated in this manual.
7
Visibility Manual
Following the Rules

## Slide 8
Progress Reports sent by the POs must include photographs and videos demonstrating visibility materials used during project activities. Photographs and videos must also show visibility material on equipment purchased under the project (if available).
Documents (analytical studies, brochures, flyers, CD, DVD, press release etc.) published under a COMCEC-funded project must include the following statement
"This [material] was prepared under the COMCEC Project Funding" on their cover (Section VI).
8
Visibility Manual
Following the Rules

## Slide 9
Every study (needs assessment reports, field study reports, situation analyses, policy recommendations, etc.) and web site prepared under a COMCEC funded project must include the following statement;
    " Views and opinions expressed in the report are solely those of the
    author(s) and do not represent the official views of the COMCEC Coordination Office or the Member States of the Organization of Islamic Cooperation.[…] (Section I, article k) "
9
Visibility Manual
Following the Rules

## Slide 10
COMCEC Logo
10
https://www.comcec.org/comcec-logo/

## Slide 11
Banner Samples
11

## Slide 12
Document Samples
12

## Slide 13
Video
13

## Slide 14
Effective
Communication
2
14

## Slide 15
Selection and communication with partner countries
  Success of the Project Implementation
  Realization of Expected Outcomes
Right after your project starts;
  Inform your partner (official letters and bilateral talks)
  Share the details of the activities and tell your expectations from your partners
Prior notification has benefits:
  Duration of internal procedures of partner countries
  Participation of right people
  Institutions to be visited and persons to be interviewed
Effective Communication
15

## Slide 16
Inform CCO with related to the preparations of project activities
Simply CC cpf@comcec.org in your communication with partner countries
Convey soft copies of official letters to CCO via e-mail
16
Effective Communication

## Slide 17
When informed on time, CCO can facilitate communication among partner countries and hence avoid potential problems beforehand
17
Effective Communication

## Slide 18
Logistical Issues and Deadlines
3
18

## Slide 19
Preparing and sending the invitation letters to prospective participants at least one month before project activities
Addressing passport and visa issues in a timely manner
Reserving flight tickets and accommodation beforehand
Arrangement of local transfers in advance
Logistical Issues
19

## Slide 20
Deadlines are determined in
  Project Implementation Guidelines
  Contract
  Detailed Work Plan
Deadlines in the Detailed Work Plan :
  Start and end dates of the main activities
  Start and end dates of the related works for the main activities
Any delay in an activity or reporting may cause:
  delay of payments
  delay of project completion (extension of project duration)
Keeping Up With the Deadlines
20
Of critical importance for planning and executing the project activities on time and properly

## Slide 21
Project Implementation Guidelines
  Detailed Work Plan: First Month
  Progress Reports: Every Month Except First Month
  Official Invitation Letters: At least one month before the event
  First Draft of Training Materials: At least one month before the date of the training program
  Final Version of Training Materials: At least two weeks before the date of the training program.
21
Keeping Up With the Deadlines
Notes: .

## Slide 22
National Ownership
4
22

## Slide 23
Ownership by the Ministries and Other Institutions of Project Owner Countries
Working in Harmony (responsible authority, contact person, project personnel and institutions of project owner countries)
Swift completion of reporting and signing procedures
Opportunity to cooperate with the Islamic world
National Ownership
23

## Slide 24
THANK you
programs.comcec.org
cpf@comcec.org